## Dashboard
Work Tracker Dashboard
As of Fri, Oct 2, 2026 ¦ Pick an owner, status or year: the whole page follows.
Owner | (All) | Status | (All) |  | Year | (All) |  |  | Showing all tasks
TOTAL TASKS |  | OVERDUE |  |  | DUE THIS WEEK |  |  |  | IN PROGRESS |  | DONE
42 |  | 7 |  |  | 6 |  |  |  | 15 |  | 9
Tasks in view |  |  | Open tasks first, then by due date ¦ 42 match the filters | [5 empty] | This Week's Focus |  | Not done, due in the next 7 days
Due | Task | Flag | Owner | Status | Priority | % done |  | Department | Due | Task | Owner | Priority | % done
2026-09-17 | Trade show booth order | OVERDUE | Casey L. | Blocked | Medium | 30% | 0.3 | Sales | 2026-10-02 | Payroll calendar 2027 | Jordan M. | Medium | 90% | 0.9
2026-09-20 | Vendor contract renewal | OVERDUE | Taylor R. | In progress | High | 70% | 0.7 | Operations | 2026-10-03 | Warehouse rack labels | Avery K. | Low | 75% | 0.75
2026-09-24 | Customer survey mailing | OVERDUE | Casey L. | In progress | Medium | 60% | 0.6 | Sales | 2026-10-04 | Quote follow-up calls | Casey L. | High | 0% | 0
2026-09-26 | Backup system test | OVERDUE | Riley P. | Blocked | High | 40% | 0.4 | IT | 2026-10-05 | Laptop refresh order | Riley P. | Medium | 55% | 0.55
2026-09-28 | Expense policy update | OVERDUE | Jordan M. | In progress | Medium | 80% | 0.8 | Finance | 2026-10-07 | Benefits enrollment memo | Morgan T. | High | 35% | 0.35
2026-09-30 | Safety training sign-off | OVERDUE | Morgan T. | Not started | High | 0% | 0 | HR | 2026-10-08 | Fleet insurance renewal | Taylor R. | High | 0% | 0
2026-10-01 | Forklift inspection | OVERDUE | Avery K. | In progress | High | 50% | 0.5 | Operations
2026-10-02 | Payroll calendar 2027 | This week | Jordan M. | In progress | Medium | 90% | 0.9 | Finance
2026-10-03 | Warehouse rack labels | This week | Avery K. | In progress | Low | 75% | 0.75 | Operations
2026-10-04 | Quote follow-up calls | This week | Casey L. | Not started | High | 0% | 0 | Sales
2026-10-05 | Laptop refresh order | This week | Riley P. | In progress | Medium | 55% | 0.55 | IT | Progress by owner |  | Follows the filters
2026-10-07 | Benefits enrollment memo | This week | Morgan T. | In progress | High | 35% | 0.35 | HR | Owner | Average % done |  | Tasks | Done | Overdue
2026-10-08 | Fleet insurance renewal | This week | Taylor R. | Not started | High | 0% | 0 | Operations | Avery K. | 0.31 | 31% | 5 | 0 | 1
2026-10-09 | Budget draft for 2027 |  | Jordan M. | In progress | High | 45% | 0.45 | Finance | Casey L. | 0.37778 | 37.78% | 9 | 2 | 2
2026-10-10 | Website contact form fix |  | Riley P. | Not started | Medium | 0% | 0 | IT | Jordan M. | 0.51875 | 51.88% | 8 | 2 | 1
+ 27 more not shown | [8 empty] | Morgan T. | 0.35714 | 35.71% | 7 | 2 | 1
[9 empty] | Riley P. | 0.41875 | 41.88% | 8 | 2 | 1
Next 5 due dates |  |  | Not done, soonest first | [5 empty] | Taylor R. | 0.42 | 42% | 5 | 1 | 1
Due | Task | Days left | Owner | Status | Priority | % done |  | Department
2026-10-02 | Payroll calendar 2027 | 0 | Jordan M. | In progress | Medium | 90% | 0.9 | Finance
2026-10-03 | Warehouse rack labels | 1 | Avery K. | In progress | Low | 75% | 0.75 | Operations
2026-10-04 | Quote follow-up calls | 2 | Casey L. | Not started | High | 0% | 0 | Sales
2026-10-05 | Laptop refresh order | 3 | Riley P. | In progress | Medium | 55% | 0.55 | IT
2026-10-07 | Benefits enrollment memo | 5 | Morgan T. | In progress | High | 35% | 0.35 | HR
+ 21 more not shown
Formulas:
OVERDUE = IF(OR(Lists!$Q4="",[TOTAL TASKS]="",[Status]="Done"),"",IF([TOTAL TASKS]<TODAY(),"OVERDUE",IF([TOTAL TASKS]<=TODAY()+6,"This week","")))

## Tasks
ID | Task | Owner | Department | Status | Priority | Start | Due | % Complete | Year | Notes
T-001 | Renew office lease | Taylor R. | Operations | Done | High | 2026-08-03 | 2026-08-28 | 100% | 2026 | Signed for 3 years
T-002 | Q3 month-end checklist | Jordan M. | Finance | Done | High | 2026-08-18 | 2026-09-04 | 100% | 2026
T-003 | Update price list | Casey L. | Sales | Done | Medium | 2026-08-23 | 2026-09-11 | 100% | 2026 | Sent to all reps
T-004 | Replace front-desk PC | Riley P. | IT | Done | Low | 2026-09-02 | 2026-09-18 | 100% | 2026
T-005 | New-hire paperwork review | Morgan T. | HR | Done | Medium | 2026-09-07 | 2026-09-23 | 100% | 2026
T-006 | Vendor contract renewal | Taylor R. | Operations | In progress | High | 2026-09-02 | 2026-09-20 | 70% | 2026 | Waiting on vendor redline
T-007 | Customer survey mailing | Casey L. | Sales | In progress | Medium | 2026-09-04 | 2026-09-24 | 60% | 2026
T-008 | Backup system test | Riley P. | IT | Blocked | High | 2026-09-12 | 2026-09-26 | 40% | 2026 | Needs a new drive
T-009 | Expense policy update | Jordan M. | Finance | In progress | Medium | 2026-09-11 | 2026-09-28 | 80% | 2026
T-010 | Safety training sign-off | Morgan T. | HR | Not started | High | 2026-09-22 | 2026-09-30 | 0% | 2026
T-011 | Forklift inspection | Avery K. | Operations | In progress | High | 2026-09-23 | 2026-10-01 | 50% | 2026
T-012 | Trade show booth order | Casey L. | Sales | Blocked | Medium | 2026-09-14 | 2026-09-17 | 30% | 2026 | Supplier out of stock
T-013 | Payroll calendar 2027 | Jordan M. | Finance | In progress | Medium | 2026-09-25 | 2026-10-02 | 90% | 2026
T-014 | Warehouse rack labels | Avery K. | Operations | In progress | Low | 2026-09-26 | 2026-10-03 | 75% | 2026
T-015 | Quote follow-up calls | Casey L. | Sales | Not started | High | 2026-09-30 | 2026-10-04 | 0% | 2026
T-016 | Laptop refresh order | Riley P. | IT | In progress | Medium | 2026-09-20 | 2026-10-05 | 55% | 2026
T-017 | Benefits enrollment memo | Morgan T. | HR | In progress | High | 2026-09-24 | 2026-10-07 | 35% | 2026
T-018 | Fleet insurance renewal | Taylor R. | Operations | Not started | High | 2026-10-01 | 2026-10-08 | 0% | 2026
T-019 | Monthly sales report | Casey L. | Sales | Done | Medium | 2026-09-22 | 2026-10-04 | 100% | 2026 | Finished early
T-020 | Budget draft for 2027 | Jordan M. | Finance | In progress | High | 2026-09-18 | 2026-10-09 | 45% | 2026
T-021 | Website contact form fix | Riley P. | IT | Not started | Medium | 2026-10-02 | 2026-10-10 | 0% | 2026
T-022 | Holiday schedule posting | Morgan T. | HR | Not started | Low | 2026-10-03 | 2026-10-11 | 0% | 2026
T-023 | Dock door repair | Avery K. | Operations | Blocked | High | 2026-09-27 | 2026-10-12 | 20% | 2026 | Part on order
T-024 | Key account review | Casey L. | Sales | In progress | High | 2026-09-29 | 2026-10-14 | 25% | 2026
T-025 | Supplier scorecards | Taylor R. | Operations | In progress | Medium | 2026-09-22 | 2026-10-15 | 40% | 2026
T-026 | Password policy rollout | Riley P. | IT | In progress | High | 2026-09-25 | 2026-10-18 | 30% | 2026
T-027 | Collections call list | Jordan M. | Finance | Not started | Medium | 2026-10-05 | 2026-10-20 | 0% | 2026
T-028 | Performance review forms | Morgan T. | HR | In progress | Medium | 2026-09-28 | 2026-10-23 | 15% | 2026
T-029 | Year-end inventory count | Avery K. | Operations | Not started | High | 2026-10-22 | 2026-10-29 | 0% | 2026
T-030 | Holiday promo flyer | Casey L. | Sales | In progress | Medium | 2026-09-30 | 2026-11-01 | 20% | 2026
T-031 | Phone system upgrade | Riley P. | IT | Blocked | Medium | 2026-09-17 | 2026-11-06 | 10% | 2026 | Carrier quote pending
T-032 | Year-end document binder | Jordan M. | Finance | Not started | High | 2026-10-12 | 2026-11-13 | 0% | 2026
T-033 | First-aid kit restock | Morgan T. | HR | Done | Low | 2026-09-20 | 2026-10-16 | 100% | 2026
T-034 | Delivery route review | Avery K. | Operations | In progress | Medium | 2026-09-26 | 2026-11-19 | 10% | 2026
T-035 | CRM cleanup | Casey L. | Sales | Not started | Low | 2026-10-16 | 2026-11-27 | 0% | 2026
T-036 | Office wifi upgrade | Riley P. | IT | Done | Medium | 2026-08-28 | 2026-09-14 | 100% | 2026
T-037 | Quarterly vendor review | Jordan M. | Finance | Done | High | 2026-09-12 | 2026-09-27 | 100% | 2026
T-038 | New-year filing setup | Jordan M. | Finance | Not started | High | 2026-12-01 | 2027-01-05 | 0% | 2027
T-039 | Server room cleanup | Riley P. | IT | Not started | Low | 2026-12-11 | 2027-01-10 | 0% | 2027
T-040 | Annual safety plan | Taylor R. | Operations | Not started | Medium | 2026-12-06 | 2027-01-15 | 0% | 2027
T-041 | Spring hiring plan | Morgan T. | HR | Not started | Medium | 2026-12-21 | 2027-01-28 | 0% | 2027
T-042 | Customer appreciation day | Casey L. | Sales | Blocked | Low | 2026-11-01 | 2027-02-04 | 5% | 2027 | Venue not confirmed

## How to use
How to use this tracker
Demo built with made-up sample data. Every task and name here is invented.
Add or change tasks
1 | Go to the Tasks sheet and type in the first empty row under the table. The table grows by itself.
2 | Status and Priority are dropdowns. % Complete takes 0% to 100%. Year fills itself in from the Due date.
3 | To remove a task, right-click its row in the table and choose Delete > Table Rows.
Read the dashboard
4 | Pick an Owner, a Status or a Year in the shaded cells at the top. Everything on the page follows. Choose (All) to clear.
5 | Overdue = not Done and the Due date is before today. Due this week = not Done and due today or in the next 6 days.
6 | Tasks in view shows up to 15 tasks, Next due dates 5, This Week's Focus 8. A line under each list says how many more are not shown.
7 | In the Tasks sheet, an overdue Due date turns red and says OVERDUE; one due this week turns amber and says so. They update by themselves, every day.
Good to know
8 | Nothing here needs macros. The file works in Excel 2010 and later, including Microsoft 365.
9 | The Lists sheet holds helper formulas for the dashboard. Leave it as it is.
10 | The sample dates were set on Oct 2, 2026, so some tasks were overdue and some due that week. The dashboard always compares with today's date, so the counts move as days pass.

## Lists
Helper lists for the Dashboard. These are formulas: please don't type on this sheet.
Dropdown choices on the left; on the right, which table row each dashboard list line shows.
Owner choices | Status choices | Year choices | # | This Week's Focus: key | Table row | # | Next due: key | Table row | # | Tasks in view: key | Table row
(All) | (All) | (All) | 1 | 46297.0001 | 13 | 1 | 46297.0001 | 13 | 1 | 46282.0001 | 12
Avery K. | Not started | 2026 | 2 | 46298.0001 | 14 | 2 | 46298.0001 | 14 | 2 | 46285.0001 | 6
Casey L. | In progress | 2027 | 3 | 46299.0001 | 15 | 3 | 46299.0001 | 15 | 3 | 46289.0001 | 7
Jordan M. | Blocked |  | 4 | 46300.0002 | 16 | 4 | 46300.0002 | 16 | 4 | 46291.0001 | 8
Morgan T. | Done |  | 5 | 46302.0002 | 17 | 5 | 46302.0002 | 17 | 5 | 46293.0001 | 9
Riley P. |  |  | 6 | 46303.0002 | 18 |  |  |  | 6 | 46295.0001 | 10
Taylor R. |  |  | 7 | [5 empty] | 7 | 46296.0001 | 11
|  |  | 8 | [5 empty] | 8 | 46297.0001 | 13
[9 empty] | 9 | 46298.0001 | 14
[9 empty] | 10 | 46299.0001 | 15
[9 empty] | 11 | 46300.0002 | 16
[9 empty] | 12 | 46302.0002 | 17
[9 empty] | 13 | 46303.0002 | 18
[9 empty] | 14 | 46304.0002 | 20
[9 empty] | 15 | 46305.0002 | 21